## Calrton Forge
ID | Finished Part Number | Forging Part Number | Nomenclature | Finished Part L (+.010" Tol.) | Finished Part ID (-.005" Tol.) | Finished Part OD (+.005 Tol.) | Material Name | Material Spec/Class | GROSS WEIGHT | Share % | 2016 QTY | 2017 QTY | EP | VSE Initiated | VSE Phase | Alternate Part L (+.010" Tol.) | Alternate Part ID (-.005" Tol.) | Alternate Part OD (+.005 Tol.) | Alternate Material Spec/Class | MACHINING SOURCE | Cut Weight (Lbs.) | LTA 2016 Price | Alternate 2016 Price | Order Received From Machining Source (Y/N) | Agreed Upon Shape (Y/N) | Billet Commit Date | Supplier Commit | First Shipment Quantity | Production Lead Time | Comments
5 | 2463M40G01 | 2463M40P02.003R | SHROUD, IGV | 2.81 | 5.837 | 10.012 | Al | AMS 4132 | 21.4 | 50 | 110 | 310 | LEAP A/C | 21006-VSE-15-02496 | 5 |  |  |  |  | B&F |  | 326 |  | N
21 | 2464M71G03 | 2464M71G03.002R | CASE, HPT | 7.135 | 24.177 | 27.003 | 718+ | C50TF128 CL-A | 334.8 | 45 | 110 | 310 | LEAP A/C | 21006-VSE-15-02497 | 4 |  |  |  |  | Avitron |  | 7923 |  | N
21 | 2464M71G03 | 2464M71G03.002R | CASE, HPT | 7.135 | 24.177 | 27.003 | 718+ | C50TF128 CL-A | 334.8 | 30 | 110 | 310 | LEAP A/C | 21006-VSE-15-02497 | 4 |  |  |  |  | Samsung |  | 7923 |  | N
42 | 2500M47P01 | 2500M47P01.000R | OGV Diffuser | 6.985 | 9.995 | 20.605 | 718+ | B50TF317 CL-A | 399 | 10 | 110 | 310 | LEAP A/C | 21006-VSE-15-02498 | 4 |  |  |  |  | TECT SF |  | 9894 |  | N
43 | 2521M40P02 | 2521M40P02.000R | HANGER, FWD | 1.937 | 22.172 | 25.895 | R41 | B50TF110 CL-D | 261.5 | 50 | 40 | 205 | Leap-1B | 21006-VSE-15-02499 | 4 |  |  |  |  | Numet |  | 3050 |  | N
45 | 2548M11G05 | 2548M11G05.002C | FINS | 2.023 | 13.997 | 17.779 | GTD222 | B50TF279 CL-C | 73.1 | 15 | 40 | 205 | Leap-1B | 21006-VSE-15-02500 | 3 | 2.117 | 13.913 | 17.876 |  | FAST |  | 1740 | 3093 | Y | Y |  | 2016-02-05 | 10 | 18 weeks
45 | 2548M11G05 | 2548M11G05.002C | FINS | 2.023 | 13.997 | 17.779 | GTD222 | B50TF279 CL-C | 73.1 | 40 | 40 | 205 | Leap-1B | 21006-VSE-15-02500 | 3 | 2.117 | 13.913 | 17.876 |  | Paradigm Malden |  | 1740 | 3093 | N | N
45 | 2548M11G05 | 2548M11G05.002C | FINS | 2.023 | 13.997 | 17.779 | GTD222 | B50TF279 CL-C | 73.1 | 25 | 40 | 205 | Leap-1B | 21006-VSE-15-02500 | 3 |  |  |  |  | Xian |  | 1740 |  | N
46 | 2548M34P01 | 2548M34P01.000R | OGV DIFFUSER | 7.117 | 9.425 | 20.425 | 718+ | B50TF317 CL-A | 398 | 10 | 40 | 205 | LEAP-1B | 21006-VSE-15-02501 | 3 |  |  |  |  | Chaheng |  | 9894 |  | Y | Y
47 | 2551M95G01 | 2551M95G01.002R | CASE, AFT INNER, STG 5 | 1.1448 | 17.4673 | 19.113 | I909 | C50TF95 CL-B | 67.3 | 25 | 40 | 205 | Leap-1B | 21006-VSE-15-02503 | 5 |  |  |  |  | PCC WB |  | 906 |  | Y | Y | 2015-11-15 | 2016-02-05 | 20 pcs | 20 weeks | order entered 9/21/15
48 | 2551M96G01 | 2551M96G01.002R | CASE, AFT INNER, STG 5-6 | 1.794 | 17.226 | 19.229 | I909 | C50TF95 CL-B | 103.3 | 25 | 40 | 205 | Leap-1B | 21006-VSE-15-02504 | 5 |  |  |  |  | PCC WB |  | 1231 |  | Y | Y | 2015-11-15 | 2016-02-05 | 22 pcs | 20 weeks | order entered 9/21/15
49 | 2551M97G02 | 2551M97G01.002R | CASE, AFT INNER, STG 6-7 | 2.389 | 17.002 | 19.289 | M152 | C50TF68 CL-B | 148.7 | 25 | 40 | 205 | Leap-1B | 21006-VSE-15-03223 | 4 | 2.422 |  |  |  | PCC WB | 151 | 551 |  | Y | Y | 2015-10-15 | 2016-02-05 | 10 | 18 weeks
50 | 2551M98G03 | 2551M98G02.002R | CASE, AFT INNER, STG 7 | 1.686 | 16.8998 | 20.623 | I718 | B50TF15 CL-E | 171.3 | 25 | 40 | 205 | Leap-1B | 21006-VSE-15-03225 | 5 |  |  |  |  | PCC WB |  | 1505 |  | N | [5 empty] | Condition of supply confirmed to PCC WB 9/9/15
50 | 2551M98G03 | 2551M98G02.002R | CASE, AFT INNER, STG 7 | 1.686 | 16.8998 | 20.623 | I718 | B50TF15 CL-E | 171.3 | 25 | 40 | 205 | Leap-1B | 21006-VSE-15-03225 | 5 |  |  |  |  | Samsung |  | 1505 |  | N
53 | 2552M49G02 | 2552M49G02.002R | CASE, AFT INNER, STG 8 | 0.9675 | 16.739 | 19.107 | I718 | B50TF15 CL-E | 106.8 | 25 | 40 | 205 | Leap-1B | 21006-VSE-15-02507 | 5 | 0.996 |  |  |  | PCC WB | 108.8 | 727 |  | Y | Y | stock | 2016-01-29 | 10 | 18 weeks | Condition of supply confirmed to PCC WB 9/9/15
54 | 2552M50G04 | 2552M50G04.002R | CASE, AFT INNER, STG 8-9 | 1.994 | 16.612 | 18.865 | I718 | B50TF15 CL-E | 120.3 | 25 | 40 | 205 | Leap-1B | 21006-VSE-15-02508 | 5 |  |  |  |  | PCC WB |  | 1142 |  | Y | Y | 2015-11-01 | 2016-03-28 | 12 | 18 weeks | order entered 9/21/15
55 | 2555M49G04 | 2555M49G04.004R | FINS | 1.734 | 14.184 | 18.335 | GTD222 | B50TF279 CL-C | 183.3 | 40 | 110 | 310 | LEAP A/C | 21006-VSE-15-02511 | 3 | 1.794 | 14.124 | 18.395 |  | FAST | 208 | 2724 | 3058 | Y | Y |  | 2016-02-05 | 5 | 16 weeks
55 | 2555M49G04 | 2555M49G04.004R | FINS | 1.734 | 14.184 | 18.335 | GTD222 | B50TF279 CL-C | 183.3 | 35 | 110 | 310 | LEAP A/C | 21006-VSE-15-02511 | 3 |  |  |  |  | Paradigm Malden |  | 2724 |  | N
56 | 2555M49G04 | 2555M49G04.003R | FINS | 1.01 | 10.433 | 12.093 | 718+ | B50TF317 CL-A | 44.4 | 35 | 110 | 310 | LEAP A/C | 21006-VSE-15-02512 | 3 | 1.055 | 10.338 | 12.16 |  | Paradigm Malden | 49 | 707 | 768 | N
58 | 2551M96G02 | 2564M04G01.002R | CASE, HPC | 1.859 | 17.761 | 19.763 | I909 | C50TF95 CL-B | 103.3 | 50 | 110 | 310 | LEAP A/C | 21006-VSE-15-02504 | 5 |  |  |  |  | GE Suzhou |  | 1884 |  | N
58 | 2551M96G02 | 2564M04G01.002R | CASE, HPC | 1.859 | 17.761 | 19.763 | I909 | C50TF95 CL-B | 103.3 | 25 | 110 | 310 | LEAP A/C | 21006-VSE-15-02504 | 5 |  |  |  |  | PCC WB |  | 1884 |  | N | [5 empty] | Condition of supply confirmed to PCC WB 9/9/15
67 | 2462M23P02 | D2462M23P02 | Outer Liner Aft Ring | 0 | 0 | 0 | HS188 | B50TF74 CL-A | 97.4 | 60 | 110 | 310 | LEAP A/C | Terre Haute | 3 |  |  |  |  | Terre Haute |  | 950 |  | N
70 | 2462M27P02 | D2462M27P02 | Inner Baffle Aft Ring | 0 | 0 | 0 | HS188 | B50TF74 CL-A | 61.4 | 40 | 110 | 310 | LEAP A/C | Terre Haute | 3 |  |  |  |  | Terre Haute |  | 171 |  | Y | Y | 2015-12-01
71 | 2462M27P03 | D2462M27P03 | Inner Baffle Fwd Baffle | 0 | 0 | 0 | HS188 | B50TF74 CL-A | 51.1 | 40 | 110 | 310 | LEAP A/C | Terre Haute | 3 |  |  |  |  | Terre Haute |  | 120 |  | Y | Y | 2015-12-01
72 | 2609M11P01 | D2609M11P01 | Domeplate | 0 | 0 | 0 | HS188 | B50TF74 CL-A | 755.4 | 50 | 110 | 310 | LEAP A/C | Terre Haute | 3 |  |  |  |  | Terre Haute |  | 5992 |  | Y | Y | 2016-01-15 | 2016-05-11 | 20 pcs | 20 weeks
81 | 2611M11P01 | D2611M11P01 | Domeplate | 0 | 0 | 0 | HS188 | B50TF74 CL-A | 744.4 | 50 | 40 | 205 | Leap-1B | Terre Haute | 3 |  |  |  |  | Terre Haute |  | 5696 |  | Y | Y | 2016-01-15 | 2016-05-06 | 3 pcs | 20 weeks
83 | 2460M47G01 | 2460M47P01.000R | SEAL, STA-CDP | 0.68 | 9.989 | 11.877 | 718plus | B50TF317 CL-A | 52.1 | 50 | 110 | 310 | LEAP A/C | 21006-VSE-15-02514 | 3 |  |  |  |  | Triumph | 61.3 | 500 |  | N | [5 empty] | requesting quote 1=2 sleeve around Triumph sketch
84 | 2460M47G01 | 2460M47P02.000R | SEAL, STA-CDP | 2.223 | 9.989 | 12.627 | I909 | C50TF95 CL-A | 48.2 | 50 | 110 | 310 | LEAP A/C | 21006-VSE-15-02515 | 3 | 2.293 | 9.874 | 12.742 |  | Triumph | 57.8 | 1104 | 1297 | N | [5 empty] | quoted new sizes to Triumph 9/9/15
86 | 2460M62G02 | 2460M62P02.000R | SEAL, STA-HPT FOS | 0.647 | 12.183 | 13.725 | GTD222 | B50TF279 CL-A | 44.8 | 20 | 110 | 310 | LEAP A/C | 21006-VSE-15-03868 | 4 | 0.73 | 11.93 | 13.81 |  | Xian | 61.4 | 569 | 718 | Y | N
86 | 2460M62G02 | 2460M62P02.000R | SEAL, STA-HPT FOS | 0.647 | 12.183 | 13.725 | GTD222 | B50TF279 CL-A | 44.8 | 50 | 110 | 310 | LEAP A/C | 21006-VSE-15-03868 | 4 |  |  |  |  | Vertechs |  | 569 |  | N | [5 empty] | confirmed condition of supply with Vertech 9/4/15
87 | 2482M35G02 | 2482M35P01.000R | SEAL, TRANS-DUCT | 0.535 | 20.013 | 22.463 | R41 | B50TF110 CL-C | 157.5 | 50 | 110 | 310 | LEAP A/C | 21006-VSE-15-02517 | 4 |  |  |  |  | Vertechs |  | 805 |  | N | [5 empty] | confirmed condition of supply with Vertech 8/27/15
89 | 2482M33G01 | 2482M33P01.000R | SEAL, HPT | 2.174 | 12.068 | 14.515 | I718 | B50TF15 CL-D | 52.4 | 50 | 110 | 310 | LEAP A/C | 21006-VSE-15-02519 | 4 |  |  |  |  | AVIO |  | 1111 |  | N
90 | 2482M33G01 | 2482M33P02.000R | SEAL, HPT | 1.446 | 14.214 | 16.111 | I718 | B50TF15 CL-D | 73.8 | 50 | 110 | 310 | LEAP A/C | 21006-VSE-15-02520 | 4 |  |  |  |  | AVIO |  | 770 |  | N
91 | 2482M30P01 | 2482M30P01.000R | FWD INNER SEAL | 1.509 | 14.696 | 17.676 | HS188 | B50TF74 CL-A | 120.4 | 50 | 110 | 310 | LEAP A/C | 21006-VSE-15-02521 | 4 |  |  |  |  | Truiumph - SanD |  | 1669 |  | N
93 | 2482M31P01 | 2482M31P01.000W | SEAL,PLATE-FW | 0.165 | 14.985 | 17.189 | R41 | B50TF110 CL-D | 72.3 | 30 | 110 | 310 | LEAP A/C | 21006-VSE-15-02651 | 5 |  |  |  |  | Triumph - SanD |  | 465 |  | N | [5 empty] | confirmed condition of supply to Triumph 9/9/15
94 | 2596M81G02 | 2596M81P01.000W | SUPPORT | 0.406 | 20.169 | 21.555 | I718 | B50TF15 CL-D | 66.8 | 40 | 110 | 310 | LEAP A/C | 21006-VSE-15-02652 | 2 | 0.556 | 20.014 | 21.71 |  | EMI | 99.3 | 360 | 490 | N
95 | 2596M81G02 | 2596M81P03.000R | SUPPORT | 0.321 | 23.357 | 26.607 | R41 | B50TF110 CL-E | 217 | 30 | 110 | 310 | LEAP A/C | 21006-VSE-15-02653 | 2 | 0.567 | 23 | 26.962 |  | EMI | 369.5 | 807 | 1294 | N
96 | 2596M86G01(will be M89) | 2596M86G01.002R | SEAL, PRESSURE BALANCE | 4.403 | 14.629 | 16.943 | I718 | B50TF15 CL-D | 125.3 | 30 | 110 | 310 | LEAP A/C | 21006-VSE-15-02654 | 4 |  |  |  |  | EMI |  | 1992 |  | N | [5 empty] | comfirmed condition of supply 8/31/15
99 | 2468M79G01 | 2468M79P01.000R | CASE,WISHBONE | 3.899 | 17.045 | 20.942 | I783 | AMS 5940 | 177.7 | 40 | 110 | 310 | LEAP A/C | 21006-VSE-15-02655 | 5 | 3.959 | 16 | 21 |  | FAST | 190 | 6003 | 6356 | Y | Y |  | 2016-02-05 | 5 | 18 weeks
100 | 2468M79G01 | 2468M79P02.000R | CASE,WISHBONE | 1.7582 | 20.5996 | 24.908 | I718 | B50TF15 CL-D | 235.8 | 40 | 110 | 310 | LEAP A/C | 21006-VSE-15-02656 | 5 | 2.17 | 20.34 | 25.02 |  | Liming | 162.2 | 2006 | 2698 | Y | Y | 2015-11-01 | 2016-02-12 | 8 | 18 weeks | order entered 9/21/15
101 | 2596M82G01 | 2596M82G01.002R | PLATE | 0.11 | 24.083 | 26.607 | R41 | B50TF110 CL-F | 198.5 | 50 | 110 | 310 | LEAP A/C | 21006-VSE-15-02657 | 4 |  |  |  |  | Liyang |  | 495 |  | N
103 | 2461M68P01 | 2461M68P01.000R | SEAL,STA.AIRB | 1.345 | 6.24 | 11.01 | I718 | B50TF15 CL-E | 83.8 | 30 | 110 | 310 | LEAP A/C | 21006-VSE-15-02658 | 4 |  |  |  |  | UEC Poland |  | 775 |  | N
109 | 2541M81G01 | 2541M81G01.002R | HPT CASE | 7.509 | 23.401 | 26.647 | 718Plus | C50TF128 CL-A | 417.8 | 20 | 40 | 205 | Leap-1B | 21006-VSE-15-02660 | 2 |  |  |  |  | TEI |  | 8549 |  | N
109 | 2541M81G01 | 2541M81G01.002R | HPT CASE | 7.509 | 23.401 | 26.647 | 718Plus | C50TF128 CL-A | 417.8 | 40 | 40 | 205 | Leap-1B | 21006-VSE-15-02660 | 2 |  |  |  |  | Samsung |  | 8549 |  | N
117 | 2547M12P01 | 2547M12P01.000R | NUT, COUPLING - HPT ROTOR | 0.985 | 4.515 | 5.113 | Inco718-PQ DM | C50TF37 CL-D | 13.7 | 30 | 40 | 205 | Leap-1B | 21006-VSE-15-02704 | 4 |  |  |  |  | Sun Country |  | 297 |  | N
118 | 2548M29P02 | 2548M29P02.000R | CASE, COMBUSTOR | 14.184 | 20.262 | 26.804 | 718Plus | C50TF128 CL-A | 1398 | 10 | 40 | 205 | Leap-1B | 21006-VSE-15-02705 | 2 |  |  |  |  | AIDC |  | 15473 |  | N
119 | 2085M68P01 | 2085M68P01.000R | CASE, COMBUSTOR | 13.501 | 20.3656 | 26.591 | 718 Plus | C50TF128 CL-A | 1278 | 10 | 110 | 310 | LEAP A/C | 21006-VSE-15-02706 | 2 |  |  |  |  | GE Suzhou |  | 15533 |  | N
120 | 2461M37P01 | 2461M37P01.000R | NUT, COUPLING HPT ROTOR | 0.98549 | 4.6026 | 5.2646 | IN718 | C50TF37 CL-D | 14.7 | 40 | 150 | 515 | Leap-1B/ AC | 21006-VSE-15-02708 | 5 |  |  |  |  | Aerocison - Chester |  | 314 |  | Y | Y | 2015-08-01 | 2015-09-15 | 10
122 | 2552M01G01 2468M16G01 | 2635M61P01 | Blisk, Aft Arm, Cmpressor Rotor | 0 | 0 | 0 | Ti 6-4 | C50TF12 CL-I | #N/A | 60 | 150 | 515 | Leap-1B/ AC | Engineer wont push through due to NNS | 0 |  |  |  |  | West Jeff |  | 1248 |  | N
124 | 2468M18G01 | 2635M64P01 | Spool, Arm Aft Cmpressor Rotor | 0 | 0 | 0 | Ti-6242 | C50TF39 CL-B | 41.8 | 60 | 110 | 310 | LEAP A/C | Engineer wont push through due to NNS | 0 |  |  |  |  | West Jeff |  | 1644 |  | N
125 | 2552M03G01 | 2468M30P02 | Spool, Arm Aft Cmpressor Rotor | 0 | 0 | 0 | Ti-6242 | C50TF39 CL-B | 65.5 | 60 | 40 | 205 | Leap-1B | Engineer wont push through due to NNS | 0 |  |  |  |  | West Jeff |  | 1793 |  | N
126 | 2482M11G01 | 4013522-470P04 | Flange, Aft TCF | 0 | 0 | 0 | I718 | B50TF15 CL-D | 450.8 | 60 | 110 | 310 | Leap-AC | 21006-VSE-15-02717 | 2 |  |  |  |  | Terre Haute |  | 4495 |  | N
127 | 2482M11G01 | 4013522-469P03 | Flange, Fwd TCF | 0 | 0 | 0 | I718 | B50TF15 CL-D | 123.8 | 50 | 110 | 310 | Leap AC | 21006-VSE-15-02724 | 4 |  |  |  |  | EMO -Direct |  | 1300 |  | N
130 | 2482M17P01 | 2482M17P01.000R | FWD HANGER | 2.025 | 23.131 | 26.592 | R41 | B50TF110 CL-D |  | 50 | 110 | 310 | LEAP A/C | 21006-VSE-15-02725 | 4 |  |  |  |  | Numet |  | 3280 |  | N
137 | 2468M80G01 | 4013726-330P02 | CASE, COMPRESSOR STATOR - AFT INNER | 1.072 | 18.0081 | 19.665 | M152 | C50TF68 CL-B | 70.8 | 25 | 110 | 310 | LEAP A/C | 21006-VSE-15-02758 | 5 |  |  |  |  | PCC WB |  | 329 |  | N | [5 empty] | confirmed condition of supply to WB 9/9/15
137 | 2468M80G01 | 4013726-330P02 | CASE, COMPRESSOR STATOR - AFT INNER | 1.072 | 18.0081 | 19.665 | M152 | C50TF68 CL-B | 70.8 | 15 | 110 | 310 | LEAP A/C | 21006-VSE-15-02758 | 5 |  |  |  |  | Samsung |  | 329 |  | N
139 | 2468M82G01 | 4013726-332P01 | CASE, COMPRESSOR STATOR - AFT INNER | 2.49 | 17.5338 | 19.765 | I718 | B50TF15 CL-E | 75.3 | 25 | 110 | 310 | LEAP A/C | 21006-VSE-15-02761 | 4 |  |  |  |  | PCC WB |  | 1450 |  | Y | Y | 2015-11-15 | 2016-02-05 | 15 pcs | 16 weeks | order entered 9/18/15
139 | 2468M82G01 | 4013726-332P01 | CASE, COMPRESSOR STATOR - AFT INNER | 2.49 | 17.5338 | 19.765 | I718 | B50TF15 CL-E | 75.3 | 25 | 110 | 310 | LEAP A/C | 21006-VSE-15-02761 | 4 |  |  |  |  | Samsung |  | 1450 |  | N
140 | 2468M83G02 | 4013726-333P01 | CASE, COMPRESSOR STATOR - AFT INNER | 1.7267 | 17.447 | 21.272 | I718 | B50TF15 CL-E | 183.8 | 25 | 110 | 310 | LEAP A/C | 21006-VSE-15-02762 | 4 |  |  |  |  | PCC WB |  | 1700 |  | Y | Y | 2015-11-15 | 2016-02-05 | 21 pcs | 16 weeks | order entered 9/18/15
140 | 2468M83G02 | 4013726-333P01 | CASE, COMPRESSOR STATOR - AFT INNER | 1.7267 | 17.447 | 21.272 | I718 | B50TF15 CL-E | 183.8 | 25 | 110 | 310 | LEAP A/C | 21006-VSE-15-02762 | 4 |  |  |  |  | Samsung |  | 1700 |  | N
142 | 2464M37P01 | 2464M37P01.000W | C-CLIP, SHROUD HIGH PRESSURE TURBIN | 0.256 | 22.768 | 22.364 | R41 | B50TF75 CL-D | 71.3 | 40 | 110 | 310 | LEAP A/C | 21006-VSE-15-04051 | 2 |  |  |  |  | Liming |  | 331 |  | N
144 | 2460M62G02 | 4013728-259P01 | SEAL, STATIONARY - HIGH PRESSURE TU | 1.147 | 12.877 | 15.623 | I783 | AMS 5940 | 79.8 | 70 | 110 | 310 | LEAP-1A | 21006-VSE-15-03844 | 4 | 1.28 | 12.72 | 15.77 |  | Vertechs |  | 1400 | 1632 | N | [5 empty] | confirmed condition of supply with Vertech 8/27/15
145 | 2548M16G01 | 4013733-958P01 | SEAL, STATIONARY - HIGH PRESSURE TU | 0.638 | 11.919 | 13.329 | GTD222 | B50TF279 CL-B | 71.3 | 25 | 40 | 205 | Leap-1B | 21006-VSE-15-02764 | 4 |  |  |  |  | Vertechs |  | 573 |  | N | [5 empty] | confirmed condition of supply with Vertech 8/27/15
145 | 2548M16G01 | 4013733-958P01 | SEAL, STATIONARY - HIGH PRESSURE TU | 0.638 | 11.919 | 13.329 | GTD222 | B50TF279 CL-B | 40.7 | 15 | 40 | 205 | Leap-1B | 21006-VSE-15-02764 | 4 | 0.72 | 11.67 | 13.41 |  | Liming | 57.4 | 573 | 693 | N
148 | 2521M46P01 | 2521M46P01.000R | SEAL, INNER- FORWARD, TRANSITION DU | 1.5745 | 14.571 | 17.135 | HS188 | B50TF74 CL-A | 104.4 | 30 | 40 | 205 | Leap-1B | 21006-VSE-15-02765 | 5 |  |  |  |  | Gentz |  | 1528 |  | Y | Y |  | 2016-04-20 | 20 pcs | 18 weeks
149 | 2521M48G01 | 2521M48P01.000R | PLATE, BACKING- AFT | 0.24 | 24.715 | 26.9616 | R41 | B50TF110 CL-D | 174 | 50 | 40 | 205 | Leap-1B | 21006-VSE-15-04055 | 2 |  |  |  |  | Triumph SanD |  | 520 |  | N | [5 empty] | confirmed condition of supply to Triumph 9/9/15
150 | 2521M49P01 | 2521M49P01.000R | PLATE, BACKING- FORWARD | 0.13 | 14.746 | 16.737 | R41 | B50TF110 CL-D | 73.3 | 50 | 40 | 205 | Leap-1B | 21006-VSE-15-04059 | 2 |  |  |  |  | Triumph SanD |  | 352 |  | N | [5 empty] | confirmed condition of supply to Triumph 9/9/15
151 | 2521M52G01 | 2521M52P02.000R | SEAL, STATIONARY- HPT STATOR | 2.185 | 10.915 | 13.807 | I718 | B50TF15 CL-D | 55.3 | 50 | 40 | 205 | Leap-1B | 21006-VSE-15-02767 | 4 | 2.265 | 10.8 | 13.992 |  | Triumph SanD | 68.3 | 1186 | 1395 | N | [5 empty] | re-quoted new sizes to Triumph 9/9/15
152 | 2521M52G01 | 2521M52P01.000R | SEAL, STATIONARY- HPT STATOR | 1.724 | 12.83 | 16.067 | I718 | B50TF15 CL-D | 117.3 | 50 | 40 | 205 | Leap-1B | 21006-VSE-15-02769 | 4 | 1.812 | 12.824 | 16.182 |  | Triumph SanD | 136.8 | 1044 | 1205 | N | [5 empty] | re-quoted new sizes to Triumph 9/9/15
154 | 2548M31G01 | 4013725-407P01 | SEAL, CDP-STATOR | 3.351 | 9.629 | 12.701 | I909 | C50TF95 CL-A | 48.7 | 50 | 40 | 205 | Leap-1B | 21006-VSE-15-02771 | 4 |  |  |  |  | Triumph SanD |  | 1646 |  | N | [5 empty] | confirmed condition of supply to Triumph 9/9/15
156 | 2552M42G05 | 2552M42P05.002C | CASE, EXTENSION COMPRESSOR STATOR - | 4.433 | 19.523 | 24.29 | I718 | B50TF15 CL-E | 279.8 | 30 | 40 | 205 | Leap-1B | 21006-VSE-15-02772 | 4 |  |  |  |  | Samsung |  | 4715 |  | N
157 | 2552M51G06 | 4013726-337P03 | CASE, COMPRESSOR STATOR - AFT INNER | 3.679 | 16.529 | 20.5 | I783 | AMS 5940 | 157.5 | 50 | 40 | 205 | Leap-1B | 21006-VSE-15-04078 | 2 | 3.91 | 16.3 | 20.57 |  | AIDC | 189.2 | 5342 | 6484 | N | [5 empty] | requoted new sizes to AIDC 8/25/15
158 | 2552M51G06 | 4013726-338P02 | CASE, COMPRESSOR STATOR - AFT INNER | 2.055 | 19.781 | 24.26 | I718 | B50TF15 CL-D | 268 | 40 | 40 | 205 | Leap-1B | 21006-VSE-15-02816 | 4 | 2.3 | 19.7 | 24.5 |  | AIDC | 158 | 2283 | 2855 | N | [5 empty] | requoted new sizes to AIDC 8/25/15
166 | 2468M83G02 | 4013726-333P02 | CASE, COMPRESSOR STATOR - AFT INNER | 1.726 | 17.455 | 21.272 | I718 | B50TF15 CL-E | #N/A | 25 | 110 | 310 | LEAP A/C | 21006-VSE-15-02817 | 4 |  |  |  |  | PCC WB |  | 1615 |  | N | [5 empty] | Condition of supply confirmed to PCC WB 9/9/15
166 | 2468M83G02 | 4013726-333P02 | CASE, COMPRESSOR STATOR - AFT INNER | 1.726 | 17.455 | 21.272 | I718 | B50TF15 CL-E | #N/A | 50 | 110 | 310 | LEAP A/C | 21006-VSE-15-02817 | 4 |  |  |  |  | Samsung |  | 1615 |  | N
167 | 2468M78G05 | 4013726-336P02 | CASE, EXTENSION, COMPRESSOR STATOR | 4.533 | 20.171 | 24.908 | I718 | B50TF15 CL-E | 292.8 | 30 | 110 | 310 | LEAP A/C | 21006-VSE-15-02818 | 4 |  |  |  |  | Samsung |  | 4850 |  | N
170 | 2521M04G04 | 2521M04P07.000C | TCF | 10.045 | 23.378 | 39.93 | I718 | C50TF37 CL-A | 3583.1 | 20 | 40 | 205 | Leap-1B | 21006-VSE-15-02819 | 3 |  |  |  |  | Ketema |  | 12685 |  | Y | Y | Carlton stock | 2015-07-08 | 5 pcs | 20 weeks
170 | 2521M04G04 | 2521M04P07.000C | TCF | 10.045 | 23.378 | 39.93 | I718 | C50TF37 CL-A | 3583.1 | 40 | 40 | 205 | Leap-1B | 21006-VSE-15-02819 | 3 |  |  |  |  | Paradigm |  | 12685 |  | Y | Y | Carlton stock | 2015-07-17 | 2 pcs | 20 weeks
170 | 2521M04G04 | 2521M04P07.000C | TCF | 10.045 | 23.378 | 39.93 | I718 | C50TF37 CL-A | 3583.1 | 10 | 40 | 205 | Leap-1B | 21006-VSE-15-02819 | 3 |  |  |  |  | FAMAT |  | 12685 |  | Y | Y | Carlton stock | 2015-07-24 | 2 pcs | 20 weeks
171 | 2521M04G04 | 2521M04P08.000R | TCF | 2.1237 | 36.215 | 43.629 | I718 | C50TF37 CL-A | 1306.5 | 20 | 40 | 205 | Leap-1B | 21006-VSE-15-02821 | 2 |  |  |  |  | Ketema |  | 7902 |  | Y | Y | Carlton stock | 2015-07-13 | 5 pcs | 16 weeks
171 | 2521M04G04 | 2521M04P08.000R | TCF | 2.1237 | 36.215 | 43.629 | I718 | C50TF37 CL-A | 1306.5 | 40 | 40 | 205 | Leap-1B | 21006-VSE-15-02821 | 2 |  |  |  |  | Paradigm |  | 7902 |  | Y | Y | Carlton stock | 2015-07-31 | 8 pcs | 16 weeks
171 | 2521M04G04 | 2521M04P08.000R | TCF | 2.1237 | 36.215 | 43.629 | I718 | C50TF37 CL-A | 1306.5 | 10 | 40 | 205 | Leap-1B | 21006-VSE-15-02821 | 2 |  |  |  |  | FAMAT |  | 7902 |  | Y | Y | Carlton stock | 2015-07-31 | 2 pcs | 16 weeks
174 | 2521M47G03 | 2521M47P02.000R | TCF Seal, Transition Duct Outer | 0.52 | 24.532 | 26.962 | R41 | B50TF110 | 193.5 | 40 | 40 | 205 | Leap-1B | 21006-VSE-15-02822 | 2 |  |  |  |  | Xian |  | 1505 |  | N

## Sheet1
Finished Part Number | ITEM NUMBER
2464M71G03 | 510757
2500M47P01 | 510758
2548M11G05 | 510759
2551M95G01 | 510760
2551M96G01 | 510761
2551M97G02 | 510762
2551M98G03 | 510763
2552M49G02 | 510764
2552M50G04 | 510765
2555M49G04 | 510766
2555M49G04 | 510767
2551M96G02 | 510768
2462M23P02 | 510769
2462M27P02 | 510770
2462M27P03 | 510771
2609M11P01 | 510772
2611M11P01 | 510773
2460M47G01 | 510774
2460M47G01 | 510775
2460M62G02 | 510776
2482M35G02 | 510777
2482M33G01 | 510778
2482M33G01 | 510779
2482M30P01 | 510780
2596M81G02 | 510781
2596M81G02 | 510782
2596M86G01 | 510783
2468M79G01 | 510784
2468M79G01 | 510785
2596M82G01 | 510786
2461M68P01 | 510787
2541M81G01 | 510788
2548M29P02 | 510789
2085M68P01 | 510790
2552M01G01 2468M16G01 | NOT ENTERED
2468M18G01 | 510792
2552M03G01 | 510793
2482M11G01 | 510794
2482M11G01 | 510795
2468M80G01 | 510796
2468M82G01 | 510797
2468M83G02 | 510798
2464M37P01 | 510799
2460M62G02 | 510800
2548M16G01 | 510801
2521M46P01 | 510802
2521M52G01 | 510803
2521M52G01 | 510804
2552M42G05 | 510805
2552M51G06 | 510806
2552M51G06 | 510807
2468M83G02 | NOT ENTERED
2468M78G05 | 510809
2521M47G03 | 510810
2463M40G01 | 510043
2521M40P02 | 510038
2548M34P01 | 510748
2482M31P01 | 510710
2547M12P01 | 501752
2461M37P01 | 510750
2482M17P01 | 510755
2521M48G01 | 510638
2521M49P01 | 510640
2548M31G01 | 510706
2521M04G04 | 510727
2521M04G04 | 510727
2521M04G04 | 510727
2521M04G04 | 510734
2521M04G04 | 510734
2521M04G04 | 510734
2464M71G03 | xxxxxxxx
2548M11G05 | xxxxxxxx
2548M11G05 | xxxxxxxx
2551M98G03 | xxxxxxxx
2555M49G04 | xxxxxxxx
2551M96G02 | xxxxxxxx
2460M62G02 | xxxxxxxx
2541M81G01 | xxxxxxxx
2468M80G01 | xxxxxxxx
2468M82G01 | xxxxxxxx
2468M83G02 | xxxxxxxx
2548M16G01 | xxxxxxxx
2468M83G02 | xxxxxxxx
new items created
new items to create
*items already in system
p/n to use in item creation

## Sheet2
ITEM NUMBER | STOCK SIZE | GROSS WEIGHT
510757 | 10 | 359
510758 | 12 | 714
510759 | 8 | 186
510760 | 6 | 66
510761 | 6 | 106
510762 | 8 | 149
510763 | 8 | 181
510764 | 6 | 103
510765 | 6 | 116
510766 | 8 | 183
510767 | 6 | 45
510768 | 6 | 114
510769 | 6 | 79
510770 | 6 | 96
510771 | 6 | 65
510772 | 12 | 741
510773 | 12 | 721
510774 | 6 | 52
510775 | 6 | 51
510776 | 6 | 48
510777 | 8 | 176
510778 | 6 | 54
510779 | 6 | 74
510780 | 6 | 121
510781 | 6 | 71
510782 | 9.5 | 239
510783 | 6 | 114
510784 | 8 | 178
510785 | 8 | 252
510786 | 9.5 | 276
510787 | 6 | 84
510788 | 10 | 404
510789 | 12 | 1398
510790 | 10 | 647
510791 | ????????? | ?????????
510792 | 6 | 42
510793 | 6 | 71
510794 | 10 | 451
510795 | 8 | 131
510796 | 6 | 71
510797 | 6 | 83
510798 | 8 | 196
510799 | 6 | 71
510800 | 6 | 80
510801 | 6 | 99
510802 | 6 | 111
510803 | 6 | 71
510804 | 6 | 147
510805 | 8 | 286
510806 | 8 | 74
510807 | 8 | 268
510808* same as 510798 | ????????? | ?????????
510809 | 8 | 298
510810 | 9.5 | 194